## Carta Gantt
Carta Gantt
Nombre Proyecto: | Khepri
Nombre Participantes: | Deyse Henriquez, Néstor Carvacho, Gary Villegas
Fecha: | 2026-08-15
Tarea | Tiempo 18 semanas lectivas (13/08/2026 – 10/12/2026)
| Semana 1 | [6 empty] | Semana 2 | [6 empty] | Semana 3 | [6 empty] | Semana 4 | [6 empty] | Semana 5 | [6 empty] | Semana 6 | [6 empty] | Semana 7 | [6 empty] | Semana 8 | [6 empty] | Semana 9 | [6 empty] | Semana 10 | [6 empty] | Semana 11 | [6 empty] | Semana 12 | [6 empty] | Semana 13 | [6 empty] | Semana 14 | [6 empty] | Semana 15 | [6 empty] | Semana 16 | [6 empty] | Semana 17 | [6 empty] | Semana 18 | [6 empty] | Semana 19
| AGOSTO | [18 empty] | SEPTIEMBRE | [29 empty] | OCTUBRE | [30 empty] | NOVIEMBRE | [29 empty] | DICIEMBRE
Día | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Fase de Planificación (Fase 1 — 20%)
Organización del equipo | JP | JP
Acta de Constitución de proyecto | JP | JP | JP | JP | JP | JP | JP | JP | JP
Aprobación del Acta | [8 empty] | JP
Planilla de requerimientos (R.1–R.45) | [7 empty] | JP | JP | JP
Matriz EDT y cálculo de esfuerzo | [7 empty] | JP | JP | JP | JP | JP | JP
Carta Gantt | [7 empty] | JP | JP | JP | JP | JP | JP
Documento Casos de uso extendido | [7 empty] | JP | JP | JP | JP | AS | AS | AS | AS | AS
Documento Mockups (capturas de la app) | [14 empty] | DG | DG | DG | DG | DG | DG | DG | DG | DG | DG | DG | DG | DG
Informe ERS (IEEE 830) | [14 empty] | AS | AS | AS | AS | AS | AS | AS | AS | AS
Documento de avance de sprints | [21 empty] | JP | JP | JP | JP | JP | JP
Presentación Fase 1 (hito 10/09/2026) | [27 empty] | DF | DF
Fase de diseño — modelo arquitectónico (Fase 2 — 20%)
Documento de arquitectura de software (DAS) | [29 empty] | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS | AS
Diccionario de datos (MySQL 8) | [35 empty] | AS | AS | AS | AS | AS | AS | AS | AS | AS
Matriz RACI | [42 empty] | JP | JP | JP | JP | JP
Matriz de riesgo | [42 empty] | JP | JP | JP | JP | JP | JP | JP | JP
Matriz de control de cambios | [47 empty] | JP | JP | JP
Hito modelo arquitectónico (01/10/2026) | [49 empty] | AS
Fase de Desarrollo (Fase 2 — 30%, 100% al 12/11/2026)
Ambiente de desarrollo (Git, .env, pytest, Vite) | [35 empty] | AS | AS | AS | DF | DF | DF
Docker Compose y despliegue Railway | [35 empty] | AS | AS | AS | AS | AS | AS | AS | AS | AS
Scripts de esquema MySQL 8 (schema_completo) | [39 empty] | AS | AS | AS | AS | AS
Módulo IAM y seguridad
R.1 Autenticar usuario (JWT) | [49 empty] | AS | AS | AS | AS | DF | DF | DF | DF
R.2 Cerrar sesión | [54 empty] | AS | DF | DF
R.3 Cambiar contraseña | [56 empty] | AS | DF | DF | DF | DF
R.4 Bloqueo por intentos fallidos | [56 empty] | AS | AS | AS
R.7 Mantenedor de usuarios | [60 empty] | AS | DF | DF | DF | DF | DF
R.8 Mantenedor de roles y permisos | [62 empty] | AS | DF | DF | DF | DF | DF
R.9 Mantenedor de cargos | [64 empty] | AS | DF | DF | DF | DF
R.10 Permisos de cargo | [67 empty] | AS | DF | DF | DF
R.27 Editar perfil de usuario | [69 empty] | DF | DF | DF
R.29 Menú y rutas según permisos | [70 empty] | DF | DF | DF
Módulo Tenant (multi-empresa)
R.5 Mantenedor de empresas | [56 empty] | AS | AS | AS | AS | DF | DF | DF | DF | DF
R.6 Filtro multi-empresa | [62 empty] | AS | DF | DF | DF | DF | DF
R.31 Aislamiento de datos por empresa_id | [63 empty] | AS | AS | AS | AS | AS | AS
Módulo Catálogo y ubicaciones
R.11 Mantenedor de productos | [68 empty] | AS | DF | DF | DF | DF | DF | DF | DF
R.12 Mantenedor de tipos de producto | [70 empty] | AS | DF | DF | DF | DF | DF
R.13 Mantenedor de unidades de medida | [72 empty] | AS | AS | DF | DF | DF
R.14 Mantenedor de bodegas | [75 empty] | AS | DF | DF | DF | DF | DF | DF | DF
R.15 Mantenedor de zonas | [77 empty] | AS | DF | DF | DF | DF | DF | DF
R.16 Mantenedor de tipos de zona | [81 empty] | AS | DF | DF | DF
Módulo Inventario operativo
R.17 Zona de recepción por bodega | [81 empty] | AS | AS | AS | AS
R.18 Consultar stock por ubicación | [82 empty] | AS | DF | DF | DF | DF
R.19 Registrar recepción | [84 empty] | AS | DF | DF | DF | DF | DF
R.20 Registrar traslado interno | [85 empty] | AS | DF | DF | DF | DF | DF
R.21 Registrar despacho | [87 empty] | AS | DF | DF | DF | DF
R.22 Historial de movimientos | [88 empty] | AS | DF | DF | DF
R.32 Escaneo de SKU en operaciones | [89 empty] | DF | DF | DF
Módulo Reportes, API y locale
R.23 Exportar stock PDF/Excel | [84 empty] | AS | AS | AS | DF | DF | DF | DF | DF
R.24 Exportar movimientos PDF/Excel | [87 empty] | AS | AS | DF | DF | DF
R.25 Filtrar listados y reportes | [88 empty] | DF | DF | DF | DF
R.26 Preferencias de locale | [88 empty] | AS | DF | DF | DF
R.28 Validaciones en formularios | [89 empty] | DF | DF | DF
R.30 API REST documentada (Swagger) | [49 empty] | AS | AS | AS | AS | AS | AS | [34 empty] | AS | AS | AS
NFR R.33–R.45 (hexagonal, HTTPS, Git, pytest, Railway) | [35 empty] | AS | AS | AS | AS | AS | AS | AS | AS | AS | [45 empty] | QA | QA | QA
Hito 100% de la(s) aplicación(es) (12/11/2026) | [91 empty] | DF
Fase de Pruebas y QA
Ambiente de pruebas | [92 empty] | QA | QA | QA | QA | QA
Pruebas funcionales por requerimiento | [95 empty] | QA | QA | QA | QA | QA | QA | QA | QA | QA | QA | QA | QA
Pruebas con usuarios (operador / jefe de almacén) | [103 empty] | QA | QA | QA | QA | QA | QA | QA | QA | QA
Plan de pruebas y registro de defectos | [95 empty] | QA | QA | QA | QA | QA | [9 empty] | QA | QA | QA | QA
Fase de implementación y cierre (Fase 3 — 30%)
Despliegue en Railway (producción académica) | [110 empty] | AS | AS | AS | AS
Manual de usuario | [110 empty] | JP | JP | DG | DG | DG | DG | DG | DG
Capacitaciones / demostración | [116 empty] | DF | DF | DF
Acta de cierre de proyecto | [117 empty] | JP | JP | JP
Entrega final Fase 3 (03/12 – 10/12/2026) | [112 empty] | JP | JP | JP | JP | JP | DF | DF | DF
NOMBRE RECURSO | SIGLA | [6 empty] | ROL
Deyse Henriquez | JP | [6 empty] | Jefa de Proyecto
Néstor Carvacho | AS | [6 empty] | Arquitecto de software / backend
Gary Villegas | DF | [6 empty] | Desarrollador frontend
Gary Villegas | DG | [6 empty] | Diseñador (mockups / UI)
Néstor Carvacho | QA | [6 empty] | Calidad y testing
NOMBRE INTEGRANTES | Nro
Deyse Henriquez | 1
Néstor Carvacho | 2
Gary Villegas | 3